## Project schedule
| Pokemon Trading Card Game Management System |  |  |  |  | Project start: | [7 empty] | 2026-07-15 | [9 empty] | Project due: | [6 empty] | Fri, 8/14/2026
[6 empty] | Display week: | [7 empty] | 1
[6 empty] | 2026-07-13 | [6 empty] | 2026-07-20 | [6 empty] | 2026-07-27 | [6 empty] | 2026-08-03 | [6 empty] | 2026-08-10 | [6 empty] | 2026-08-17 | [6 empty] | 2026-08-24 | [6 empty] | 2026-08-31
| TASK | PROGRESS | START | END | time axis 2026-07-13 to 2026-09-06
 | time axis 2026-07-13 to 2026-09-06
Do not delete this row. This row is hidden to preserve a formula that is used to highlight the current day within the project schedule.
Investigate
| Project Shedule (create gantt chart) | 100% | 2026-07-15 | 2026-07-15 | 1
| Problem Outline | 100% | 2026-07-15 | 2026-07-15 | 1
| Problem Description | 100% | 2026-07-15 | 2026-07-16 | 2
| List of functional and non-functional requirements | 100% | 2026-07-16 | 2026-07-16 | 1
| List of ethical, legal and security considerations | 100% | 2026-07-16 | 2026-07-16 | 1
| Collect data on pokemon cards etc | 100% | 2026-07-16 | 2026-07-17 | 2
Design
| ERD | 100% | 2026-07-17 | 2026-07-17 | 1
| Data Dictionary | 100% | 2026-07-17 | 2026-07-18 | 2
| List of SQL queries | 100% | 2026-07-18 | 2026-07-19 | 2
| structure chart for python program | 100% | 2026-07-19 | 2026-07-20 | 2
| Function specification for each major function | 100% | 2026-07-20 | 2026-07-22 | 3
Develop
| SQL script that creates complete database structure and populates it | 100% | 2026-07-23 | 2026-07-25 | 3
| Python application and its functions | 100% | 2026-07-26 | 2026-08-02 | 8
| Functions performing sql queries | 100% | 2026-08-03 | 2026-08-10 | 8
Testing and Evaluation
| Test using appropriate test data | 100% | 2026-08-11 | 2026-08-11 | 1
| Evaluate and check if requirements are met | 100% | 2026-08-12 | 2026-08-12 | 1
| Identify strengths and limitations | 100% | 2026-08-12 | 2026-08-12 | 1
| Suggest future improvements | 100% | 2026-08-12 | 2026-08-12 | 1
| Specify where AI was used | 100% | 2026-08-12 | 2026-08-12 | 1 | bar: 2026-09-01
Insert new rows ABOVE this one

## Data Dictionary
Field Name | Data Type | Field Size | Key Type | Description | Constraints
PlayerID
Username
DateJoined
DateOfBirth
PhoneNumber
Email
TournamentsEntered
MatchesPlayed
MatchesWon
Cards
PlayerID
CardID
Quantity
CardID
CardName
CardType

## About
SIMPLE GANTT CHART by Vertex42.com
About This Template
This template provides a simple way to create a Gantt chart to help visualize and track your project. Simply enter your tasks and start and end dates - no formulas required. The bars in the Gantt chart represent the duration of the task and are displayed using conditional formatting. Insert new tasks by inserting new rows.
Guide for Screen Readers
There are 2 worksheets in this workbook. TimeSheet About The instructions for each worksheet are in the A column starting in cell A1 of each worksheet. They are written with hidden text. Each step guides you through the information in that row. Each subsequent step continues in cell A2, A3, and so on, unless otherwise explicitly directed. For example, instruction text might say "continue to cell A6" for the next step. This hidden text will not print. To remove these instructions from the worksheet, simply delete column A.
Additional Help
Click on the link below to visit vertex42.com and learn more about how to use this template, such as how to calculate days and work days, create task dependencies, change the colors of the bars, add a scroll bar to make it easier to change the display week, extend the date range displayed in the chart, etc.
How to Use the Simple Gantt Chart
More Project Management Templates
Visit Vertex42.com to download other project management templates, including different types of project schedules, Gantt charts, tasks lists, etc.
Project Management Templates
About Vertex42
Vertex42.com provides over 300 professionally designed spreadsheet templates for business, home, and education - most of which are free to download. Their collection includes a variety of calendars, planners, and schedules as well as personal finance spreadsheets for budgeting, debt reduction, and loan amortization.
Businesses will find invoices, time sheets, inventory trackers, financial statements, and project planning templates. Teachers and students will find resources such as class schedules, grade books, and attendance sheets. Organize your family life with meal planners, checklists, and exercise logs. Each template is thoroughly researched, refined, and improved over time through feedback from thousands of users.